C++ Rate Limiter Service — Project Plan

Reference: original one-page project brief (scope, functional/non-functional requirements, suggested endpoints, and acceptance criteria AC1–AC7). This plan starts from the requirements only — no implementation exists yet.

1. Purpose

This document lays out the system's structure at a high level, then divides and sequences the implementation work across the team before any code is written. It is meant to be edited as the plan firms up.

2. Scope Recap (from the brief)

- Accept requests identified by a key (user ID, API key, or IP).

- Track request counts/tokens in memory for the MVP (Token Bucket Criteria).

- Support configurable limits (N requests per time window).

- Return allow/deny decisions with remaining quota metadata.

- Provide a basic endpoint to inspect current limiter status.

- Out of scope for MVP: distributed rate limiting, Redis, dashboards, authentication, persistent storage.

3. Architecture Overview (Abstraction)

Before assigning tasks, here is the high-level shape of the system: three layers, each with one responsibility, talking only to the layer directly below it.

| Layer | Component | Responsibility |
| --- | --- | --- |
| API layer | HTTP server (httplib) + route handlers | Receives HTTP requests, parses/validates input, calls into the logic layer, formats the HTTP response (status code + JSON body). Does not itself decide allow/deny or store any state. |
| Logic layer | Bucket class (one instance per key) | Owns the rate-limiting algorithm for a single key: current token count, refill calculation based on elapsed time, and the allow/deny decision. Thread-safe on its own (one lock per bucket). |
| Storage layer | Rate_Limiter / Store class | Owns the in-memory map of key -> Bucket. Handles key generation (with collision checking), looking up a bucket for a given key, and creating new buckets. Thread-safe on its own (one lock protecting the map structure). |

The four endpoints and which layer/class they call into:

| Endpoint | Calls into | Purpose |
| --- | --- | --- |
| POST /key_request | Rate_Limiter::issue_new_key | Generate a new key, create its bucket with default limits, return the key to the caller. |
| POST /check | Rate_Limiter::find + Bucket::check_and_consume | Evaluate and consume one unit of quota for a given key; return allow/deny plus remaining quota. |
| GET /status/{key} | Rate_Limiter::find + Bucket::peek | Read-only: report current limit/remaining for a key without consuming anything. |
| POST /config | Rate_Limiter::find + Bucket::reconfigure | Update the limit/refill settings for an existing key. |

4. Team & Ownership

Each layer above maps directly to one owner, so the interface between layers (Phase 1 below) is the main thing to agree on up front.

| Owner | Layer | Scope (maps to overview above) |
| --- | --- | --- |
| Reham | API layer | Set up httplib, wire up the four routes, request parsing/validation, status codes, response shape. Calls into whatever interface Youssof exposes from the logic/storage layer. Maps to AC2, AC3, AC5 and the brief's "Suggested Endpoints." |
| Youssof | Logic & storage | Implement the Bucket class (algorithm + refill math) and the Rate_Limiter/Store class (in-memory key -> Bucket map, key generation, thread safety). Exposes a small interface for Reham to call from the API layer. Maps to AC1, AC4, AC6 and the brief's "Track request counts/tokens in memory" and "Window reset / refill." |
| Ghoneam | Testing | Once a working build exists, manual testing of the logic classes directly, plus system testing by connecting to the running service's port. Owns verification against every acceptance criterion, AC1–AC7. |

5. Proposed Phases

Phases 2 and 3 can run in parallel once the interface is agreed in Phase 1 -- Reham can build the API layer against a stub while Youssof builds the real logic behind it, so neither is blocked waiting on the other.

| Phase | Work | Owner(s) | Depends on |
| --- | --- | --- | --- |
| 1 | Agree on the architecture overview above (layers, classes, endpoint contract) so both sides start from the same interface -- e.g. what Bucket::check_and_consume returns, exact field names in requests/responses. | Whole team | Project brief |
| 2 | Implement Bucket (algorithm + refill) and Rate_Limiter/Store (map + key generation + locking). | Youssof | Phase 1 |
| 3 | Set up httplib, implement the four route handlers calling into Phase 2's classes (can start against a stub interface in parallel with Phase 2). | Reham | Phase 1 |
| 4 | First working build: compiles, all four endpoints reachable, happy-path manual curl checks pass. | Reham & Youssof | Phases 2 and 3 |
| 5 | Full testing pass against AC1–AC7, including a genuine concurrency script for AC4 (not manual one-at-a-time curl calls). | Ghoneam | Phase 4 |
| 6 | Fix issues found in Phase 5, re-test, write the README / build & run instructions (AC7). | Whole team | Phase 5 |

6. Deliverables by Owner

| Owner | Deliverables |
| --- | --- |
| Reham | Httplib & Json Header Files integrated and building; four working endpoints matching the agreed contract; input validation and clear error responses (AC5); consistent status codes and response fields (limit, remaining, retry/reset info per AC3). |
| Youssof | Bucket class implementing the chosen algorithm's state and refill logic, thread-safe; Rate_Limiter/Store class implementing thread-safe in-memory storage of one bucket per key, with collision-checked key generation. |
| Ghoneam | A completed AC1–AC7 checklist with pass/fail and notes; a script (not manual curls) for the AC4 concurrency test; the project's README with build and run instructions (AC7). |

7. Acceptance Criteria Checklist

To be worked through once Phase 4 (first working build) is reached. Concurrency (AC4) specifically requires a script firing simultaneous requests, since manual one-at-a-time testing cannot produce a genuine race condition.

| AC | Criterion (from project brief) | How Ghoneam will verify |
| --- | --- | --- |
| AC1 | Valid request within limit is allowed and returns success. | Request a key, then check once with it -> expect success response. |
| AC2 | Request exceeding the configured limit is blocked with 429. | Call check repeatedly past the configured limit -> expect 429 on the request that exceeds it. |
| AC3 | Response includes limit, remaining, and retry/reset info. | Inspect a blocked response body for limit, remaining, and retry/reset fields. |
| AC4 | Concurrent requests do not corrupt counters or over-allow. | Fire many simultaneous check calls at one key with a script and confirm the allowed count never exceeds the configured limit. |
| AC5 | Invalid or missing key is rejected with a clear error. | Call check with no key, an empty key, and an unknown key -- expect a clear error each time, never a silent/empty response. |
| AC6 | After window reset/refill, requests become allowed again. | Drain a bucket, wait past the reset interval, check again -> expect it to be allowed. |
| AC7 | Build and run instructions are provided; project compiles. | Follow the README from a clean checkout and confirm it compiles and runs with no undocumented steps. |

8. Open Decisions

- Which algorithm to implement for the MVP: fixed window, sliding window, or token bucket (brief allows any of the three).

- Exact endpoint names and field names (the brief's suggested endpoints are a starting point, not fixed).

- Default limit values (capacity / refill rate or window size) to ship with for the demo.

This plan is a living document — update ownership, phase status, and open decisions as the team agrees on them.